## Sheet1
Risk | Likelihood | Impact | Detection Difficulty | When | Risk Response | Who is Responsible | Contingency Plan
miscommunication between project manager and programmar about developing Requirements | 3 | 5 | 4 | During development | Avoiding: Ensure all team members are aware of the requirements | Nazifa[Project Manager]
misunderstanding about events requirement | 3 | 4 | 4 | After marketing | Avoiding: Ensure all requirements are covered | Nazifa[Project Manager],Victor[CEO]
slow response of API | 4 | 3 | 4 | Post installation | Avoiding:Using better tested API's from beginning | Vihar[Programmer]
Change Authority Certification by 3rd party APIs | 4 | 3 | 1 | Post installation | Avoiding: Using better tested API's from the beginning | Vihar[Programmer]
Targeted users number according the Marketing Strategy fails | 4 | 4 | 2 | After marketing | Mitigating: Find loopholes in the strategy | Victor[CEO] | Hire more experienced marketing team
Programmer Resigning | 5 | 5 | 1 | Any point of time | Transfering: Contract | Ikeade[CFO] | Enforce Contract
Vendor change the requirements | 3 | 2 | 1 | Any point of time | Transfering: Need to find another vendor | Ikeade[CFO]
Hardware failure | 4 | 4 | 3 | Any point of time | Avoiding:fixing that hardware | Hardware team
lose vendor because of last miniute change in Time frame | 3 | 3 | 1 | During marketing | Avoiding:try to follow time frame | Vihar[Programmer]